## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Any other metrics defined in your SPPP
0 | 05/10/2022-05/16/2022 | Definition of Product has been scoped, Team has an idea of architecture to be utilized going forward, Team has taken initiatives on POCs | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1 | 05/17-05/23 | Completion of base framework for backend and frontend | Integration issues with auth0 implementation | Learning for ndoejs framework | Faster share of resources | 3 | 1 | 1 | 0 | 0 | 55 | 58 | 31 | 19 | 10 | 6.5 | 6 | 4 | 9.5 | 3
1 | 5/24 - 05/31 | Integration of Auth0 ,Migrations for database structure | Dependency issues with nodejsjs and auth0 | Sync up timing |  | 3 | 1 | 1 | 0 | 0 | 61 | 52 | 33 | 21 | 1.5 | 10.5 | 12 | 3 | 2.5 | 0.5
2 | 5/31-6/14 | 1. wrote tests for User, UserMenuItem components, About page ,SortBySelect ,JobForm and NavMenuItems 2.Complete the frontend, backend and database for the feature add job, add activities | backend was not in the first week at this iteration |  | The backend issue fixed | 6 | 0 | 0 | 0 | 0 | 130.5 | 115.5 | 15 | 36 | 1 | 2 | 46 | 12 | 5.5 | 9
3 | 06/14-06/20 | 1.Completion of Deployment 2.Completion of Project Completion |  |  |  | 6 | 0 | 0 | 0 | 0 | 70.5 | 65.5 | 5 | 2.5 | 1 | 9 | 31 | 8 | 6.5 | 7

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
Chinmay Bhelke | i. Overview ii Non Functional Requirements iii. Risk Management iv. Deployment Plan | i. Low Level Requirement Analysis for Application Components | i. Software Architecture & Diagram ii. Database Design iii. Security Design iv. Business Logic (not diagram only content) v. Design Patterns | - | Final Demo | Frontend , Backend , Middleware | React App Unit Test for Authentication | Setting up Starter Code and Deployment | Attended all meetings , regular communication | Meeting Mintues
Taina Conde | i. Part of Overview ii. Related Work iii. Configuration Management plan iv. Timeline v. Part of Proposed high-level requirements vi. Revision History | i. Created 3 user stories - Login user, create user and color system | i. Introduction ii. Redux MVC part of Software Architecture & Redux Diagram iii. UI Design iv. Business Logic - Sequence diagram |  | i. Iteration 0 presentation ii. Iteration 2 presentation iii. iteration 2 demo iv. implementation part of final presentation | Frontend | BasicModal test JobForm test | set up Redux | set an agenda for most of the meetings, communicate with team members about the UI designs, asked questions about requirements, communicate with Chinmay about implementation | Meeting Mintues
Benoît Clemenceau | Quality Assurance Plan: Metrics Coding Standard Code Review Process Testing Defect Management | Created 2 user stories: Add a Job to track, Update Job | Reviewed it | All of it: Testing Summary Manual Testing Report (+ external CS673_STD_Manual_Testing_Report_team2 file) Automated Testing Report Testing Metrics Report | Final presentation testing part | Tests | JobCardNew.test NoJobs.test NavMenuItems.test User.test UserMenuItem.test About.test | Set up Jest + React-Testing-Library | Attended all meetings, regular communication
Ruiqi Chang | Functional Requirments | Created 2 user stories: Add a timeline; Update Job activity Manage the all stories status Use case diagram | Class Diagram UI design |  | iteration 1 demo implementation part of final presentation | Frontend: -About page -Mission page |  |  | Attended all meetings, regular communication | Meeting Mintues
Bharat Gogineni | i. Overview ii Non Functional Requirements iii. Timeline | Created 2 user stories: Add a timeline for each task Notification Service | Code Refactoring Backend Business Logic |  | Iteration 3 Demo Final Presentation Project Management Final Presentation Design | Code Refactoring |  | Setup Backend | Attended all meetings , regular communication

## studentName (hidden)
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6

## BenoitClemenceau
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: QA Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 10 | 6 | 4 | 0 - Learned what QA is, what are good metrics to track, how to track them, reviewed different types of tests, testing frameworks/librairies, reviewed branching strategies 5 - Discussed branching strategy 6 - Set up Git repo & client | 5 |  |  |  |  | 0.5 | 0.5 |  | Quality Assurance Plan SPPP section | 1. Didn't know much about QA 2. Had to figure out why I could't use my Git client | 1. Have a good general understanding of it now, need to start implementing tests to confront it to real-life scenarios 2. Found why, solved | 4 - Start writing tests 5 - Start implementing QA metrics 6 - Set up test environment | 12
2 | 05/17-05/23 | 9 | 9 | 0 | 0 - studied course material, did quiz 1 and lab 2 1 - wrote 2 user stories (Add a Job to track, Update Job) 4 - did research on Selenium and started playing with unit tests 5 - caught up weekly meeting, read meeting minutes and written reports from my teammates | 4 | 1 |  |  | 2 | 2 |  |  |  | 5 - couldn't go to the weekly meeting because was at the graduation ceremony | 5 - caught up | 4 - Start writing tests 5 - Start implementing QA metrics 6 - Set up test environment | 11
3 | 05/24 - 05/31 | 9 | 6 | 3 | 0 - did more research about the different testing frameworks and which one would be best with our current stack, learned React components unit testing 4 - Set up Jest testing framework for front-end + back-end | 3 |  |  |  | 3 |  |  |  | Did STD Updated SPPP |  |  | Write tests Setup Continuous Testing | 11
4 | 06/01 - 06/07 | 14 | 12 | 2 | 0 - continued learning about tests, particularly Jest & React-Testing-Library (config with typescript, querying, matchers, mocking functions and components, best practices) 4 - wrote tests for User & UserMenuItem components + About page (all 100% coverage & passing) 6 - Fixed Babel, Jest, and JS-DOM config for TypeScript; enabled Jest coverage reports for all files; created utils/test-utils.tsx wrapper for tests | 6 |  |  |  | 4 |  | 2 |  |  |  |  | - PR - Write more tests - Setup Continuous Testing - Add Nonfunctional testing - Update SPPP & STD | 17
5 | 06/08 - 06/14 | 6 | 5 | 1 | 0 - Did research about Nonfunctional testing 4 - Added tests for SortBySelect & NavMenuItems 6 - Created a Pull Request | 3 |  |  |  | 1 |  | 1 |  | - SPPP: updated Quality Assurance Plan part - STD: Manual tests and automated Testing reports |  |  | - STD: Testing manual section details, Negative Testing - Add picture to about page - Write more tests: validation tests, contact Taina if I need help - Setup Continuous Testing - Add Nonfunctional testing - Update SPPP & STD - Prepare testing prez part - Film prez part on Zoom et envoyer a Bharat before monday 3PM | 7
6 | 06/15 - 06/21 | 4 | 3 | 1 | 4 - Added tests for JobCardNew & NoJobs, Added Nonfunctional testing with Lighthouse |  |  |  |  | 3 |  |  |  | - STD: added a proper Manual Testing Report page with 6 new manual tests including one negative test, updated metrics reports - Presentation: testing |  |  |  | 7

## ChinmayBhelke
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: QA Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 10 | 6 | 4 | 0 -Learned about Risk Management and Authentication 1 - Defined high level non functional requirements 3 - Launched starter project and implemented beginning logic and user flow , planning for all infra involved 6 - set up git t dependencies , launch initial project build for frontend 7 - Perform risk analysis document , test started project , complete git changes | 5 |  |  |  |  | 0.5 | 0.5 |  | SPPP Risk Assessment , Contributions to sections from SPPP for Team | 1. Had to get familiar with Risk Management Principles 2. No other major issuies | 1. Have a good general understanding of it know, need to start implementing tests to confront it to real-life scenarios 2. Found why, solved | 1 - Start Implementing CSS , HTML , JS for Project 2 - Implemented Routes and push development branches to git 3 - Set up tasks on PivotalTracker 4 - Set up server on Backend and set up API Routes | 10
2 | 05/17-05/23 | 12 | 16 | 24 | 0 - Did some learning and Practice with Redux Toolkit Caching and Optimistic Updates and tested some REST routes and read Class Modules Planned for Next Project Iteration Deliveable and completed Quiz 1 and Lab 2 1 - Did Analysis on Required Components and Class Entity Analysis for Objects for the application 2 - Completed System Design Work and drafted a high level design of the flow of the application and the system 3 - Implemented sample functionality for Auth and implemented Caching and some frontend logic for the application. Setup the backend server and implemented JWT authentication from frontend to backend 4 - Tested some REST Routes and tested all of the implementation efforts I was involved with 5 - Connected with some other teammates and collaborated on the Dev environment and planned next work to be done 6 - Completed Risk Analysis Document and added some risk items and provided updates on all the items with new insight and set up dev environment Pushed personal branch to Github and launched backend Express server and shared SSH key with everyone | 5 | 1 | 1 | 3 | 2 | 3 | 1 | 0 | SPPP Risk Assessment , Contributions to sections from SPPP for Team Implementation and Design Set up Backend Server in AWS Account , setup NodeJS and mySQL on the Server Implemented Auth and setup starter template for Project Created branch on Github and pushed code | 5 Need to setup better communication with teammates and work together with them to sync everyone on ongoing efforts | 5 - Created plan to address better plan moving forward | 2 - Design Backend and help with integration 3 - Setup and integrate all API Routes and integrate with Frontend Logic , Polish up frontend for Production 4 - Learn and implement Unit Tests for Frontend and Backend Code and pick up some testing frameworks | 12
3 | 05/24-05/30 | 12 | 11.5 | 24 | 0 - Did some learning on Design Patterns , Caching , Distributed Architecture , and basic unit tests 1 - Reviewed and analyzed some of the proposals for UI design proposed by the team 3 - Continued with implementation for frontend and setting up REST API's 5 - Coordinated with team to setup activities | 6 | 1 | 1 | 3 | 0 | 0.5 | 0 | 0 | Contributed to Sections from SDD for System Design , Software Architecture , Key Algorithms , Security Design. Added diagrams and Pseudocode explanations where necessary. Completed Risk Assessment document and continued working on the application implementation and design. Studied distributed system concepts and design patterns and analyze our application for design patterns | 5 All team members were not familiar with each others work and stack so we spent some time syncing on these items5 | 5 - Adjusted scheduled and meeting plans accordingly to allow for extra time | 2 - Add polishing touches and CSS to frontend and focus on backend optimization 3 - Setup and integrate all API Routes and integrate with Frontend Logic , Polish up frontend for Production 4 - Validate unit tests are setup correctly and give correct results 5- Focus on deployment and making sure users can access application | 8
4 | 05/30-05/05 | 20 | 20 | 1 | 0 - Learning about JWT RSA Validation and Go Postgres CRUD 2 - Implemented and made changes to frontend design based on DB structure 3 - Implementation of REST API's and frontend code lots of small things had to be implemented 5 - | 4 | 0 | 1 | 15 | 0 | 0 | 0 | 0 | Contributed towards most sections of SDD and implemented the entire backend and requirement analysis doc | 5 - No communication from group member , missing work | 5 - Not a major issue - completed work myself and setup meetings with team | 2 - Add CSS to React components and update design docs for backend 3 - Setup remaining API Routes for CRUD 4 - Validate unit tests are setup correctly and give correct results 5- Focus on deployment and making sure users can access application | 20
5 | 06/05-06/13 | 25 | 28 | 1 | 0 - Learning on Asynch JS calls , caching , REST API Design , Microservices architecture , 2 - Requirement analysis for remaining tasks and dividing work between team members 3 - Continued with frontend and backend development , setup logs for backend and added features to frontend and backend 5 - Communicated with team and set up tasks 6 - Setup plan for PROD deployment of final assignment | 5 | 0 | 1 | 20 | 0 | 1 | 1 | 0 | Contributed by creating entire backend and most sections from SDD including diagrams and requirement analysis doc. Setup communication between all team members and followed up with members about missing work | 5 - No communication from group member , missing work | 5 - Worked on missing deliverables | 2 - Work on finishing touches for design and upload new diagrams for updated SDD , SPPP docs 3 - Integrate new API Routes and share logic with rest of the team 4 - Validate unit tests are setup correctly 5- Setup CICD pipeline for deployment | 20
56 | 06/14-06/20 | 15 | 15 | 1 | 0 - Deployment to Vercel and updating Authorization to accept calls from Deployed Origin 2 - Requirement analysis for final tasks remaining for project 3 - Finishing touches and extra features for project frontend and backend 5 - Communicated with team and set up tasks 6 - Setup plan for final tasks and communicated ideal timeline of tasks | 2 | 0 | 3 | 5 | 0 | 2 | 3 | 0 | Contributed by creating entire backend and most sections from SDD including diagrams and requirement analysis doc. Setup communication between all team members and followed up with members about missing work | No major issues for Final Week | In a good state for final deployment | Final Week | 15

## BharatGogineni
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Team Leader,Backup QA
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 9 | 5 | 4 | 0 - NodeJS Unit Testing Frameworks 2 - Nodejs Express based framework design with Unit testing structure 5 - Talk to team members on project testing ideas and backend framework 6 - set up git environment and unit testing environment 7 - Documentation and presentation notes | 1 |  | 2 |  |  | 1 | 0.5 | 0.5 | 1. Add documentation into SPPP 2. Set up git, lab1 initial commit 5. Participate in Iteration 0 presentation | 1 |  | 0- Cleaner framework for setting node environment,Research how to perform integration testing 2 - Create base structure for nodejs environment and mock database 4 - setup nodejs cleaner | 8
2 | 05/17-05/23 | 12 | 15 | 3 | 0 - Research and setup zest framework 2 - Completed System Design Work on backend and created a level design of the flow of the application and the system 3 - Setup the backend server and implemented JWT authentication backend 4 - Tested some REST Routes and tested all of the implementation efforts I was involved with 5 - Connected with some other teammates and collaborated on the Dev environment and planned next work to be done 6 - Updated Progress Report and tracking | 5 | 0 | 1 | 3 | 2 | 3 | 1 | 0 | SPPP Prgress Report, Contributions to sections from SPPP for Team Implementation and Design Set up Backend Server in AWS Account , setup NodeJS and mySQL on the Server Implemented Auth and setup starter template for Project Created branch on Github and pushed code | 5 Explaining backend code took a while,Estabilishing migrations was a little harder than initially though | 5 - Sharing a of resources | 2 - Design Backend and help with integration 3 - Setup and integrate all API Routes and integrate with Frontend Logic , Polish up frontend for Production 4 - Learn and implement Unit Tests for Frontend and Backend Code and pick up some testing frameworks | 12
3 | 05/24-05/30 | 12 | 10.5 | 2 | 0 - Did some learning on Design Patterns , Caching , Distributed Architecture , and basic unit tests 2 - Reviewed /Restructured backend implementations 3 - Continued with implementation for backend and created up REST API's 5 - Communicated some future plans and suggestions with the rest of the team and expressed some concerns | 6 | 0 | 1 | 3 | 0 | 0.5 | 0 | 0 | Contributed to SPPP and Database design. Studied distributed system concepts and design patterns and analyze our application for design patterns | 5 Schedule was hectic this week so didn't have time to sync with team mates | 5 - Re adjust team meeting time | 2 - Full Integration with frontend and backend 3 - Setup and integrate all API Routes and integrate with Frontend Logic , Add Test cases annd deploy 4 - Validate unit tests are setup correctly and give correct results 5- Focus on deployment and making sure users can access application | 8
4 | 05/30-05/05 | 10 | 6 | 1 | 0 - Learning about JWT RSA Validation and Modified nodejs Structure to suit auth0 2 - Implemented and made changes to backend application 3 - Cleanup nodejs application and create mock tests for db 5 - | 4 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | Contributed towards most sections of SDD and implemented the entire backend and requirement analysis doc | 3 - Nodejs Implementation for auth0 not very well documented ran into issues | 5 - Not a major issue - completed work myself and setup meetings with team | 2 - Add CSS to React components and update design docs for backend 3 - Setup remaining API Routes for CRUD 4 - Validate unit tests are setup correctly and give correct results 5- Focus on deployment and making sure users can access application | 6
5 | 06/05-06/13 | 12 | 8 | 1 | 0 - auth0 jwt implementation nodejs backend 2 - Requirement analysis for remaining tasks and dividing work between team members 3 - Continued with frontend and backend development , setup logs for backend and added features to frontend and backend 5 - Communicated with team and set up tasks | 2 | 0 | 1 | 3 | 0 | 1 | 1 | 0 | Contributed by creating entire backend and most sections from SDD including diagrams and requirement analysis doc. Setup communication between all team members and followed up with members about missing work | 5 - Ran into timing issues with Graduation | 5 - Worked on missing deliverables | 2 - Work on finishing touches for design and upload new diagrams for updated SDD , SPPP docs 3 - Integrate new API Routes and share logic with rest of the team 4 - Validate unit tests are setup correctly 5- Setup CICD pipeline for deployment | 8
56 | 06/14-06/20 | 14 | 14 | 1 | 2 - Requirement analysis for final tasks remaining for project 3 - Finishing touches and extra features for project frontend 5 - Communicated with team and set up tasks 6 - Setup plan for final tasks and communicated ideal timeline of tasks | 0 | 0 | 3 | 6 | 0 | 2 | 3 | 0 | Contributed by restructuring front end and cleanup and refactoring,Helped compile Presentation video Setup communication between all team members and followed up with members about missing work | No major issues for Final Week | In a good state for final deployment | Final Week | 14

## RuiqiChang
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Requirement Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 9 | 5 | 4 | 0 - Learn git documentation including Git command and Github Desktop. study how to push my commit in GitHub. Learn more knowledge about React and pivotal track 5 - Discuss with team member about branch and some though on the project. Work on Meeting Mintues and reflect the problem of first meeting. 6 - set up gitHub envirnment, work on lab1 report. | 2 |  |  |  |  | 2 | 1 |  | 1. Write Meeting Mintues file 2. set up gitHub, work on lab1 report | 1. not familar with working with other developers using Git and GitHub 2. Some concept of the project file are confuesd 3. The time of Team meeting was over expectation | 1. watch some videos and resuorse about Git and GitHub 2. Search this concept on web or send email to prof. 3. Set a concise meeting agenda | 0 - Go over TypeScript because I did not have experience on that 1 - Decide the user story 2 - Decide design and impletation plan and assign to each team member | 15
2 | 05/16-05/23 | 10.5 | 8.5 | 2 | 0-Learning the class material and UI design for web 1-Wrote two user story( add timeline and add job activities) and working on lab 2 2-Try to implement Taina's UI design on Figma which is a vector graphics editor and prototyping tool 5-Discuss with team member about backend of project. Reflect and revise the problem of first iteration 6-try to set up AWS | 2 | 3 | 2 |  |  | 0.5 | 1 |  |  | Can't get the group AWS instance | search more video and ask team member | -Complete UI design with Taina -Complete SDD -Start work on backend | 20
3 | 05/23-05/30 | 10 | 7.5 | 2.5 | 0-Read the React and TypeScript 2-Implement Taina's UI Mockups on Figma and the class digram 5-Discuss with team member about backend of project. Work on the SDD 6-connected to AWS 7-demo for the iteration1 project | 3 |  | 2.5 |  |  | 1 | 0.5 | 0.5 | 1. SDD: class digram part and UI design 2. demo video | 1.did not manage my time well because this week is the first week of my summer intern 2.did not communcate with teammember well on backend parts | 1.arrange my time well and communate with team member more 2. Weekly meeting will be in the early week day. | -Work on backend | 15
4 | 05/30/-06/06 | 14 | 12.5 | 1.5 | 0-Read and learn the JEST test for our test 1-Management the poivet tasks 5-Discuss with team member about backend of project. Work on the comments in SDD, SPPP, and STD 7-Lab3 | 8 | 0.5 |  |  |  | 1 |  | 3 | 1. Meeting Mintues 2. Managed the poivet | 1.did not communcate with team member well on backend parts | 1. Weekly meeting will be in the early week day. | -Work on interation 2 doc | 5
5 | 06/06-06/13 | 5 | 3.5 | 1.5 | 1-Management the poivet tasks 5-Discuss with team member new front and backend update of project. Work on the SDD, SPPP and meeting Minutes |  | 0.5 |  |  |  | 3 |  |  | 1. SDD, SPPP 3. Managed the poivet | None |  | -Work on the land page on front end | 5
6 | 6/13-6/20 | 13.5 | 12.5 | 1 | 0- Learn Use Case Diagram 1- Management the poivet tasks 3- About Page and Mission page 5-Discuss with team member new front and backend update of project. Work on the SDD, SPPP and meeting Minutes 7-Final Presentation -requirement anlysis | 0.5 | 1 |  |  | 8 | 2 | 1 |  | 1. About and Mission page 2. Final presentation video 3. Managed the poivet | None

## TainaConde
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Configuration Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 14.5 | 10.5 | 4 | 0 - study project documentation, watch explanatory videos about project docs, read git documentation, study how to make pull requests and merge branches in GitHub, study branches strategies 5 - talk to team members about branching strategies, add some thoughts on project overview. Based on Chinway risk management sheet, write Management Plan section on SPPP 6 - work on project configuration plan, set up gitHub team repository, create branch lab1, work on lab1 report, merge team members changes to main 7 - prepare presentation | 5 |  |  |  |  | 2 | 3 | 0.5 | 1. Write 2 sections of SPPP and add some thoughts in other sections 2. set up gitHub team repository, create branch lab1, work on lab1 report, merge team members changes to main 3. Participate in Iteration 0 presentation | 1. not familar with working with other developers using Git and GitHub 2. Project documentation is extensive, had to study carefully to make sure I understood the assignment 3. Meeting could have been more objective, but I understand because it was the first meeting. | 1. I'm reading Git and GitHub docs on pull requests and branching. By the end of the next week I will be more confortable with that. 2. Concluded 3. Set an agenda for the next meeting and assign someone as the time keeper. | 0 - review typescript guidelines 1 - define requirements 2 - define design | 10
2 | 5/16 - 05/23 | 11.5 | 9.5 | 2 | 0 - study typescript documentation, Class diagrams tools 1 - write 2 user stories related to user authentication (user log in and create account) and work on lab2 assignment 2- draw mockups by hand related to user log in UI and create account UI 5 - Show mockups to team, set an agenda for this week's meeting, write this weeks meeting minutes | 3 | 5 | 0.5 |  |  | 1 |  |  | 1 - write this week's meeting minutes | 1 - We couldn't see what was wrong with the calculation on the risk management sheet | 1 - watch the progress report video again. Found out what was wrong. Concluded. | 1- Look for graphic mock up tools for design 2 - Design some UI mockups with Ruiq 3 - start developing the User Authentication with rest of the team 4 - update SPPP with the rest of the team 5 - Write STD and SDD with the rest of the team | 12
3 | 5/24 - 05/31 | 18 | 16.5 | 1.5 | 0 - read styled-components documentation, study MVC architecture, study sequence diagrams 1 - Update requirements in SPP: add color system, followup alert and customizable configurations. Rewrite Usability 2 - degin UI mockups and write SDD UI design section 3 - implement Navbar, JobCard, AddBtn, DeleteBtn, HomePageHeader, UserMenuItem, SortBySelect components in front-end 5 - Set an agenda for this weeks meeting, show UI design to team members 7- Update SPP accordingly to feedback: write paragraphs about differences between FollowUp and Huntr | 3 | 0.5 | 6 | 6 |  | 0.5 |  | 0.5 | 1 - write Overview, MVC part in software architecture, UI Design, and Business Logic sections of SDD 2 - Draw MVC and sequence diagrams on Lucidcharts 3 - implement front-end components Navbar, JobCard, AddBtn, DeleteBtn, HomePageHeader, UserMenuItem, SortBySelect, NavMenuItems and styles related to these components 4- Update SPP Related Work section. Update requirements | 1 - Noticed that our branches names are confusing | 1 - I will talk to the group to define a naming convention for the branches | 1 - Change the UI designs to expand card when clicked 2 - do more tests for the front end 3 - implement another feature our team is going to decide on. | 15
4 | 5/31 - 06/07 | 16 | 13.5 | 2.5 | 0 - learn how to test react components with Jest. Read react testing-library documentation. 3 - implement the BasicModal component 4 - test BasicModal component. Write lab3 report. 5 - Set an agenda for the week's meeting. | 4 |  |  | 5 | 4 | 0.5 |  |  |  | 1- The backend built so far isn't working | 1- Chinmay will create a backup backend so we can test the front end | 1- set up redux to manage app ui 2 - set up api requests from the front end using RTK query 3 - create form component to add a new job 4 - make the "add a job to track" functionality work with the backend | 16
5 | 06/07 - 6/14 | 22 | 21 | 1 | 0 - Study how to test forms. Read and learn Formik implementation. Study Redux toolkit implementation. 3 - implement the "add a job to track" functionality by creating the JobForm component and using the BasicModal component to display the form to the user. Implement JobForm component with Formik. 4 - Write unit tests for the JobForm component 6 - Set up Redux toolkit to manage app state and RTK query to handle api requests. 7 - Update iteration timeline on SPPP. Do presentation and Demo | 6 |  |  | 6 | 3 |  | 5 | 1 | 1 - Participated creating the frontend part of the "add a job to track" functionality with other team members 2 - Connect front end and backend though api requests using RTF query 3- add Card color system user story to pivotaltracker 4 - Update iterations timeline on SPPP 5 - record presentation and demo videos |  |  | 1 - Work on the Edit/ update job card user story 2 - Work on the Card Color system | 18
6 | 6/14 - 6/21 | 22 | 21 | 1 | 3 - Implement color system feature, think about the logic to change card's color, define the card's style 5 - set meeting agenda, comunicate with Chinmay about feature implementation 7 - Update iteration timeline on SPPP and links. Do implementation part of final presentation |  |  |  | 20 |  | 0.5 |  | 0.5 | 1 - Participated creating the frontend part of the "color system" functionality with Chinmay Bhelke 4 - Update iterations timeline on SPPP and add links 5 - record implementation part of final presentation 6 - meeting minutes for meeting 6