## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Any other metrics defined in your SPPP
0 | 05/10/2022-05/16/2022 | Definition of Product has been scoped, Team has an idea of architecture to be utilized going forward, Team has taken initiatives on POCs | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1
2
3

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments

## studentName
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6

## BenoitClemenceau
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: QA Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 10 | 6 | 4 | 0 - Learned what QA is, what are good metrics to track, how to track them, reviewed different types of tests, testing frameworks/librairies, reviewed branching strategies 5 - Discussed branching strategy 6 - Set up Git repo & client | 5 |  |  |  |  | 0.5 | 0.5 |  | Quality Assurance Plan SPPP section | 1. Didn't know much about QA 2. Had to figure out why I could't use my Git client | 1. Have a good general understanding of it know, need to start implementing tests to confront it to real-life scenarios 2. Found why, solved | 1 - Set up test environment 2 - Start implementing QA metrics 3 - Start writing tests | 10

## ChinmayBhelke
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: QA Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 10 | 6 | 4 | 0 -Learned about Risk Management and Authentication 1 - Defined high level non functional requirements 3 - Launched starter project and implemented beginning logic and user flow , planning for all infra involved 6 - set up git t dependencies , launch initial project build for frontend 7 - Perform risk analysis document , test started project , complete git changes | 5 |  |  |  |  | 0.5 | 0.5 |  | SPPP Risk Assessment , Contributions to sections from SPPP for Team | 1. Had to get familiar with Risk Management Principles 2. No other major issuies | 1. Have a good general understanding of it know, need to start implementing tests to confront it to real-life scenarios 2. Found why, solved | 1 - Start Implementing CSS , HTML , JS for Project 2 - Implemented Routes and push development branches to git 3 - Set up tasks on PivotalTracker 4 - Set up server on Backend and set up API Routes | 10

## BharatGogineni
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Team Leader,Backup QA
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 9 | 5 | 4 | 0 - NodeJS Unit Testing Frameworks 2 - Nodejs Express based framework design with Unit testing structure 5 - Talk to team members on project testing ideas and backend framework 6 - set up git environment and unit testing environment 7 - Documentation and presentation notes | 1 |  | 2 |  |  | 1 | 0.5 | 0.5 | 1. Add documentation into SPPP 2. Set up git, lab1 initial commit 5. Participate in Iteration 0 presentation | 1 |  | 0- Cleaner framework for setting node environment,Research how to perform integration testing 2 - Create base structure for nodejs environment and mock database 4 - setup nodejs cleaner | 8

## TainaConde
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Configuration Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 14.5 | 10.5 | 4 | 0 - study project documentation, watch explanatory videos about project docs, read git documentation, study how to make pull requests and merge branches in GitHub, study branches strategies 5 - talk to team members about branching strategies, add some thoughts on project overview. Based on Chinway risk management sheet, write Management Plan section on SPPP 6 - work on project configuration plan, set up gitHub team repository, create branch lab1, work on lab1 report, merge team members changes to main 7 - prepare presentation | 5 |  |  |  |  | 2 | 3 | 0.5 | 1. Write 2 sections of SPPP and add some thoughts in other sections 2. set up gitHub team repository, create branch lab1, work on lab1 report, merge team members changes to main 3. Participate in Iteration 0 presentation | 1. not familar with working with other developers using Git and GitHub 2. Project documentation is extensive, had to study carefully to make sure I understood the assignment 3. Meeting could have been more objective, but I understand because it was the first meeting. | 1. I'm reading Git and GitHub docs on pull requests and branching. By the end of the next week I will be more confortable with that. 2. Concluded 3. Set an agenda for the next meeting and assign someone as the time keeper. | 0 - review typescript guidelines 1 - define requirements 2 - define design | 10

## RuiqiChang
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Requirement Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 9 | 5 | 4 | 0 - Learn git documentation including Git command and Github Desktop. study how to push my commit in GitHub. Learn more knowledge about React and pivotal track 5 - Discuss with team member about branch and some though on the project. Work on Meeting Mintues and reflect the problem of first meeting. 6 - set up gitHub envirnment, work on lab1 report. | 2 |  |  |  |  | 2 | 1 |  | 1. Write Meeting Mintues file 2. set up gitHub, work on lab1 report | 1. not familar with working with other developers using Git and GitHub 2. Some concept of the project file are confuesd 3. The time of Team meeting was over expectation | 1. watch some videos and resuorse about Git and GitHub 2. Search this concept on web or send email to prof. 3. Set a concise meeting agenda | 0 - Go over TypeScript because I did have experience on that 1 - Decide the user story 2 - Decide design and impletation plan and assign to each team member | 15