## Sheet1
This sheet provides some common risks in student projects. You should check if it applies to your group project. You should also feel free to add other risks. Exemplary analysis is also added.
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
Personnel | Loss of team members | One or more team members drop the class | 2 | 4 | 4 | 4*2*4=32 | team leader and all members | 2022-06-01 | Redefine the project scope if necessary, and assign the tasks to other team members. | No one dropped the class so far | Open
| Adding New Team Members | Adding a new person to the team to take on tasks for the project | 1 | 4 | 3 | 12 | All Members | 2022-05-16 | Will require onboarding of a new team member | No need to add new team members | Open
| Lack of motivation or responsibility | Team member(s) are not motivated to perform tasks required for the project | 1 | 2 | 2 | 4 | All Members | 2022-05-16 | Will require realloation of duties and responsibilities | Responsibilities and deliverables are currently well assigned | Open
| Inability to Perform Assigned Work | Tasks are Assigned to members who do not possess the required prerequisite knowledge to perform tasks on time | 1 | 5 | 3 | 15 | Responsible Members | 2022-05-16 | Will require realloation of duties and responsibilities | Team has regular meetings and frequent communication. Responsibilities and deliverables are currently well assigned | Open
Communication | Duplicate Work | Team Members perform duplicate work and work on items that another team member has already worked on | 1 | 1 | 1 | 1 | Responsible Members | 2022-05-16 | Need to improve communication between team members and make sure tasks are completed by appropriate team members | The group project is structured and we have communication channels set up and tasks are well defined | Open
| Worked on Wrong Components | Team Members work on the wrong components for work assigned | 2 | 3 | 1 | 6 | Responsible Members | 2022-05-16 | Team members perform work on the incorrect component / task assigned to them | Team has regular meetings and frequent communication. Responsibilities and deliverables are currently well assigned | Open
| Inconsistent Work | Team Members do not consistently perform assigned work for the duration of the project | 5 | 3 | 1 | 15 | All Members | 2022-05-16 | Responsible members are not consistently meeting expectations and responsibilities to complete required tasks | Currently there is no sample data and initial tasks have kicked off to a productive start | Open
Requirements | Unclear Requirements | Responsibilities to complete all deliverables are not clear and work is not properly assigned | 2 | 2 | 3 | 12 | All Members | 2022-05-16 | The group as a whole is not establishing clear requirements for required tasks for the project | The group has a clear structrure and proper communication channels and everyone is working together to help with doubts and make sure all requirements are clear. There is a dedicated requirements leader for the group | Open
| Scope Creep | Additional / Unplanned tasks arise that have been unaccounted for related to the Project | 5 | 5 | 5 | 125 | Implementation Engineer (Chinmay) | 2022-05-16 | Proper planning has to be completed and the implementation lead should proactively plan for all possible tasks and situations | The team is actively planning for future potential requirements that may arise | Open
| Constant Requirement Changes | Requirements constantly change related to the project and tasks for team members | 1 | 5 | 2 | 10 | All Members | 2022-05-16 | Develop a process to ensure requirements are constant and every team members responsibilities have clarity | The group has a clear structrure and proper communication channels and everyone is working together to help with doubts and make sure all requirements are clear. There is a dedicated requirements leader for the group | Open
Management | Improper Task Assignment | Tasks are not assigned to the correct individuals or certain tasks are left unassigned | 1 | 5 | 4 | 20 | All Members , Team Lead | 2022-05-16 | Ensuring that all tasks are reviewed and all team members are comfortable with performing the assigned tasks | Tasks have been properly assigned after reaching a group consensus with regular communication | Open
| Lack of Management Skills | The team / responsible members do not have good management skills | 1 | 5 | 5 | 25 | Team Lead (Bharat) | 2022-05-16 | The individuals responsible for management do not have the appropriate management skills | The project and group lead has global enterprise experience with leadership and is very knowledgable about best leadership and management practices | Open
Technology competence | Not familiar with the framework used | Team Members are not familiar with frameworks used for the project | 1 | 3 | 4 | 12 | Implementation Engineer (Chinmay) | 2022-05-16 | Tasks should be assigned depending on individuals level of comfort with the required technology stack | The group has determined comfortable aspects of the tech stack we are using and work is being performed accordingly | Open
| Not familiar with the programming language used | Team Members are not familiar with frameworks / languages used for the project | 1 | 3 | 4 | 12 | Implementation Engineer (Chinmay) | 2022-05-16 | Tasks should be assigned depending on individuals level of comfort with the required technology stack | The group has determined comfortable aspects of the tech stack we are using and work is being performed accordingly | Open
| Not familiar with unit testing | Team Members are not familiar with testing practices used for the project | 2 | 3 | 4 | 24 | All Members | 2022-05-16 | Tasks should be assigned depending on individuals level of comfort with the required testing stack | The group has certain members with some testing experience and the rest of the members are actively learning about testing | Open
| Not familiar with Git | Team Members are not familiar with git and CICD | 1 | 3 | 3 | 9 | Responsible Members | 2022-05-16 | Tasks should be assigned depending on individuals level of comfort with the required testing stack | All Team Members have working knowledge and comfortability with Git | Open
Design and implementation | Improper design | The project is not designed properly to deliver a quality final product | 1 | 5 | 5 | 25 | Implementation Engineer (Chinmay) | 2022-05-16 | Make sure all components of the project interact with each other properly and the design supports a robust and responsive application | Lots of thought has been put into the design implications of the different components involved | Open
| improper technology stack | The technology used for the project is not appropriate | 1 | 5 | 5 | 25 | Responsible Members | 2022-05-16 | The improper technology stack has been used for the components involved in the project | The team is following software best practices and borrowing from past experiences to choose appropriate technologies for components | Open
| Messy code | The Code is not understandable and is difficult to read | 3 | 4 | 2 | 24 | All Engineers | 2022-05-16 | The code for the project is messy and not understandable by facilitators and other team members | The team is using Typescript for the project and defining types and isolating components and responsibilities in order to have clean code | Open
Testing | Not enough testing | Proper Testing has not been implemented for the project | 3 | 3 | 3 | 27 | Responsible Members | 2022-05-16 | Testing has not been implemented for the project and appropriate docs and unit testing is not included | The team is actively working on ensuring proper testing is being implemented for the project | Open
Integration and deployment | Not enough time for integration and deployment | There is not enough time left to integrate and deploy the project | 1 | 5 | 5 | 25 | Implementation Engineer (Chinmay) | 2022-05-16 | The team runs out of time to properly integrate and deploy the project | The Engineers are proactively setting up deployment and CICD and regularly redeploying the application through iterations to avoid this risk | Open